## Sprint
Column1 | Column2 | Column3 | Column4 | Column5
Planning document: Black Heritage Society of WA
Retrospective of Week #2
Tasks | Estimate | Assigned to | Issue # | Notes
Sprint 1: Sept. 29 - Oct. 3
Server/Setup/Permissions/Users | 4 hrs | Curtiss
WordPress Install | 3 hrs | Team
Github sync setup | 3 hrs | Team
Client Interview Notes | 3 hrs | Eric
Interview Client | 1 hrs | Team |  | Carry over next week to finish up interview
Create Client Staging Area | 2 hrs | Lia
Create Project Proposal | 2 hrs | Lia
Requirements Document | 3 hrs | Monisha
Submitted/Uploaded Weekly Assignments | 1 hrs | Danny
Sprint 2: Oct. 6 - 10
Build tasks: LESS/Grunt | 2 hrs | Team
WordPress Install/Permissions/Users | 2 hrs | Team |  | Carried over from last week
Github sync | 1 hrs | Team |  | Carried over from last week
Basic theme layout | 5 hrs | Lia/Eric
Basic styling concepts | 3 hrs | Dev Team
Information architecture w/client | 2 hrs | Design Team |  | Carried over from last week
Plugin research/planning/installation: |  | Dev Team
PayPal/Back Ups | 3 hrs | Monisha
Security/Forms | 3 hrs | Curtiss
SEO | 3 hrs | Danny